Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 30 September 2026 |
| --- | --- |
| Team ID | SWTID-2026-7125 |
| Project Name | AI Study Buddy API |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a user, I can register for the application by entering my email, password, and confirming my password. | 2 | High |  |
| Sprint-1 | Login | USN-2 | As a user, I can log into the application by entering email & password. | 1 | High |  |
| Sprint-1 | API Access | USN-3 | As a developer, I can generate and manage an API key so that I can securely call the Study Buddy API. | 3 | High |  |
| Sprint-1 | Explain Topics | USN-4 | As a student, I can send a topic to /explain and get a clear explanation with an example. | 5 | High |  |
| Sprint-1 |  | USN-5 | As a student, I can choose my level (beginner / intermediate / advanced) so that the explanation matches my understanding. | 3 | High |  |
| Sprint-1 | API Access | USN-6 | As a developer, I get clear error messages and rate limiting so that the API is reliable and fair to use. | 3 | High |  |
| Sprint-1 | Documentation | USN-7 | As a developer, I can read Swagger / Postman API documentation so that I can integrate quickly. | 3 | Medium |  |
| Sprint-2 | Practice Quizzes | USN-8 | As a student, I can generate a quiz from a topic so that I can test my understanding. | 5 | High |  |
| Sprint-2 |  | USN-9 | As a student, I receive instant feedback and explanations on my quiz answers. | 3 | High |  |
| Sprint-2 |  | USN-10 | As a student, I can ask for a hint instead of the full answer so that I learn by thinking. | 2 | Medium |  |
| Sprint-2 | Summarize Notes | USN-11 | As a student, I can paste text and get a short summary with key points. | 3 | High |  |
| Sprint-2 |  | USN-12 | As a student, I can upload a PDF of notes and get a summary of its key formulas and definitions. | 5 | Medium |  |
| Sprint-2 | Safety | USN-13 | As a parent or teacher, I want unsafe or age-inappropriate content to be blocked so that students stay safe. | 2 | High |  |
| Sprint-3 | Study Plan | USN-14 | As a student, I can enter my exam date and topics to get a day-by-day study plan. | 5 | High |  |
| Sprint-3 |  | USN-15 | As a student, I can mark weak topics so that the plan gives them more time. | 3 | Medium |  |
| Sprint-3 | Progress Tracking | USN-16 | As a student, I can see my quiz history and progress over time. | 3 | Medium |  |
| Sprint-3 | Language Support | USN-17 | As a student, I can get explanations in my own language (for example Tamil or Hindi). | 3 | Medium |  |
| Sprint-3 | Explain Topics | USN-18 | As a student, I get answers based on my uploaded notes with the source passage shown. | 4 | Medium |  |
| Sprint-3 | Performance | USN-19 | As a developer, I get faster responses for common questions through caching. | 2 | Low |  |
| Sprint-4 | Dashboard | USN-20 | As a developer, I can view a dashboard of my API usage, limits and errors. | 5 | Medium |  |
| Sprint-4 | Practice Quizzes | USN-21 | As a student, I can create flashcards from my notes for quick revision. | 3 | Low |  |
| Sprint-4 | Testing | USN-22 | As a team, we complete user acceptance testing and fix reported bugs. | 5 | High |  |
| Sprint-4 | Deployment | USN-23 | As a team, we deploy the API to the cloud with HTTPS and monitoring. | 4 | High |  |
| Sprint-4 | Documentation | USN-24 | As a team, we finalize the documentation and demo of the project. | 3 | High |  |

Total: 24 user stories, 80 story points across 4 sprints (20 points per sprint).

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 05 Oct 2026 | 10 Oct 2026 |  |  |
| Sprint-2 | 20 | 6 Days | 12 Oct 2026 | 17 Oct 2026 |  |  |
| Sprint-3 | 20 | 6 Days | 19 Oct 2026 | 24 Oct 2026 |  |  |
| Sprint-4 | 20 | 6 Days | 26 Oct 2026 | 31 Oct 2026 |  |  |

Velocity:

Each sprint lasts 6 days and the team’s velocity is 20 story points per sprint. The team’s average velocity (AV) per iteration unit (story points per day) is:

AV = Sprint velocity / Sprint duration = 20 / 6 ≈ 3.33 story points per day

At this velocity, the 80-point backlog is planned to finish in 4 sprints (24 days).

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

Figure 1: Planned burndown. Add the actual remaining points after each sprint day to compare.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts